## Tasks
# S. No | WBS ID | Task Name | Duration in Days/Hrs | Start Date | End Date | Work in Hrs | Resource Name | Status
Scope: All COC Backlog Tickets to be cleared
| 1 | Backend Tasks |  | 2024-06-25 | 2024-06-28
| 1.1 | ZC-4572-->IIS monitoring Graphs should display if we have the monitoring plugin for the windows instances |  | 2024-06-25 | 2024-06-28 |  | Deepak
| 1.2 | ZC-4554-->Frontend May month and June Month Date Change for Zoom View and Cloud connect byte conversion testing |  | 2024-06-25 | 2024-06-28 |  | Deepak
| 1.3 | ZC-4538-->Staging (COC) =>Home > Manage > Zoom-view > Graph > there is No data for any Instances in the Staging.but for the Same Instances in dev there is an Presence of data there in the API itself there is no data. |  | 2024-06-25 | 2024-06-28 |  | Yogashree
| 1.4 | ZC-4481-->In Admin -> Bill summary -> Total value is showing wrong. |  | 2024-06-25 | 2024-06-28 |  | Ashok
| 1.5 | ZC-4335-->In Dev(COC) => Home > Dashboard → the Instances Ip Address is wrong the API Data itself is wrong here, invalid Private Ip format. This comes under the Virtual Instances. |  | 2024-06-25 | 2024-06-28 |  | Yogashree
| 1.6 | ZC-4280-->In Admin -> Cloud Connect -> Alice Blue Customer -> Usage -> For the two routers available in West 2 and Chennai, the usage data is incorrect. |  | 2024-06-25 | 2024-06-28 |  | Deepak
| 1.7 | ZC-4211-->Dev(COC) => Home > Reports > Ip Tracking & Top Apps & Geo Traffic there is an Presence of the Common CSV File to send the Reports to the Respective mails. with no Report. |  | 2024-06-25 | 2024-06-28 |  | Deepak
| 1.8 | ZC-4159-->Dev(COC) => Home > Manage > Zoom-View > Graph > The graph data is getting Hidden when we hover on it. |  | 2024-06-25 | 2024-06-28 |  | Yogashree
| 1.9 | ZC-4144-->Dev(Admin) => Home > Billing > Bill Summary > Consolidated Bills > Clicking on the Invoice Button > Display the Popup and in that Popup Clicking on the Create Invoice Anyways Button the API is showing "504 Gateway Time out". error. |  | 2024-06-25 | 2024-06-28 |  | Deepak
| 2 | ZC-4135-->Dev(Admin) => Home > Customer > View > Sub Customer > Subscriptions> Add Renew Button > The Start date & Expiry date is of Wrong and it is getting Accepted. |  | 2024-06-25 | 2024-06-28 |  | Yogashree
| 2.1 | ZC-4132-->Dev(COC) => Home > Manage > Zoom-view > Graph > Selecting Instances Button it is displaying the API, but it is duplicated |  | 2024-06-25 | 2024-06-28 |  | Deepak
| 2.2 | ZC-4024-->In dev -> firewall -> unused port is showing wrong. |  | 2024-06-25 | 2024-06-28 |  | Yogashree | To be Closed
| 2.3 | ZC-3236-->UAT-ADMIN > VM Master > if we add a LAN IP and submit the data and again view the instances LAN IP is missing |  | 2024-06-25 | 2024-06-28 |  | Deepak
| 2.4 | ZC-3197-->In UAT-COC=>Dashboard >Instance duplicate values is showing |  | 2024-06-25 | 2024-06-28 |  | Yogashree
| 2.5 | ZC-2724-->UAT->coc-Reports-Top Apps when iam downloading csv file its getting download to zybisys email even its showing in mail but report is not coming to email |  | 2024-06-25 | 2024-06-28 |  | Deepak
| 2.6 | ZC-2715-->CoC --> Cloud Connect --> NSE Message Per Second in Exchange interface IP Wise |  | 2024-06-25 | 2024-06-28 |  | Yogashree
| 2.8 | ZC-2353-->Production-->Dashboard instances count and manage instances counts are not matching |  | 2024-06-25 | 2024-06-28 |  | Deepak
| 2.9 | ZC-72-->Dashboard CoC |  | 2024-06-25 | 2024-06-28 |  |  | To be Closed
| 2 | Frontend Tasks |  | 2024-06-25 | 2024-06-28
| 2.1.1 | ZC-4560-->In COC -> UAT -> Dashboard -> Download csv file -> In the file its showing Backup Availabe, but currently there is no backup available in coc.Remove this column in csv file. |  | 2024-06-25 | 2024-06-28 |  | Manimegalai
| 2.1.2 | ZC-4358-->In Dev(COC) => Home > Manage > Instance > Clicking on the Notifications it is Displaying the State as “Unknown”. |  | 2024-06-25 | 2024-06-28 |  | Arun
| 2.1.3 | ZC-4315-->Dev(Admin) => Home > Coc Panel > Cloud Connect > usage > while hovering on the graph the graph is displaying the data but in API it is showing empty. |  | 2024-06-25 | 2024-06-28 |  | Dharun
| 2.1.4 | ZC-2577-->Dev admin--->customer screen three dots In View if i click “remove as primary “it is not functioning |  | 2024-06-25 | 2024-06-28 |  | Arun
| 3 | QA Tasks |  | 2024-06-25 | 2024-06-28
| 3.1.1 | ZC-4580-->Make necessary changes and correction in the CXO report's overall performance section |  | 2024-06-25 | 2024-06-28 |  | Ajet | To be Closed
| 3.1.2 | ZC-4575-->Report Frontend screen changes Integration with backend functionality |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.3 | ZC-4493-->1. Reports-->Geo Traffic Logic Change to as per the current requirement 2. Manage-->Zoom View-->Internet-->Geo Traffic Section |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.4 | ZC-4468-->In Dev-> Coc -> Lama Report -> For system, Network, Application, Database, IP'S is not showing. |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.5 | ZC-4461-->COC/COC-Admin/Vendor -> Cloud Connect -> Usage -> Bandwidth Graph -> Calculations should be done using 1000-bits method |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.6 | ZC-4458-->COC/COC-Admin/Vendor - Zoomview -> Graph -> Implement interface bandwidth graph in bit i.e. conversion will be implemented using 1000 |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.7 | ZC-4325-->In dev(Admin) => Home > Coc-Panel > Zoom-view > Customer & Data-center Clicking on Chennai West-3 it is displaying the data of Mumbai West-2. |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.8 | ZC-4214-->Dev(COC) => Home > Manage > Zoom-view > Services & Graph & Internet in Zebu Customer with the location of mumbaiWest-1 there is an Presence of the Duplicated Ip. |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.9 | ZC-4171-->Firewall NOC Dashboard New requirements |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.10 | ZC-4142-->Dev(COC) => Home > Manage > Zoom-View > Internet > Internet Activities > Apps > Spelling mistakes Mismatching to UI to CSV File. |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.11 | ZC-3989-->DEV > VENDOR (or) PARTNER page > Dashboard > while comparing DEV and Vendor page, for the instances data is mismatching |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.12 | ZC-3955-->In DEV-vendor=> Firewall page is in loading state |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.13 | ZC-3943-->In DEV-vendor=> Table header name and data is mis-matching with API and UI |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.14 | ZC-3924-->In DEV-COC and DEV-vendor=>Here CPU and Memory is missing |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.15 | ZC-3048-->UAT-COC- BILLING >Invoices >In view PDF > Amount total in words missing the indication like ( : = - ). |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.16 | ZC-2902-->UAT=>Reports-Ip tracking if iam selecting one month data its showing network error |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.17 | ZC-2723-->UAT coc--> Reports-ip tracking-when iam clicking on main csv file iam getting network error |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.18 | ZC-2712-->Dev coc=> manage-zoomview-internet-internetactivities -graph-if i click on mode another screen is opening but when i scroll down instnace name and ip address are getting disabled |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.19 | ZC-2695-->Dev coc---> for the aliceblue customer-chennai west-1 location dashboard data its showing , but if i check in firewall overview its not showing data |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.20 | ZC-2694-->Dev admin---> coc panel-instnaces-for the tradejini customer for the west one location in admin side its showing only but it should be like 25 instnaces |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.21 | ZC-2665-->Dev coc--->manage-zoomview-internet-in internet screen if i click on session flow i select ip and the timing interval is 15 minutes iam getting a network error. |  | 2024-06-25 | 2024-06-28 |  | Ajet
| 3.1.22 | ZC-2648-->In admin panel -> VM MASTER -> if i select the location, ex:- west 2, then in customer dropdown also it will come only for west2 customers. |  | 2024-06-25 | 2024-06-28 |  | Ajet